## Sheet1
| Team Members: | Maksim
Mikhail
Nam
Aldorino
NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE 1 | [19 empty] | PHASE 2 | [19 empty] | Stu Vac |  |  |  |  | PHASE 3
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 | [9 empty] | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Phase 1
1 | Team formation | EVERYONE | 2025-07-28 | 2025-08-24 | 26 | 100%
1.1 | Role Distribution | Maksim | 2025-07-28 | 2025-08-24 | 26 | 100% | bar: WEEK 1 R to WEEK 4 F; WEEK 6 R
1.2 | Git, Trello, WA, Drive setup | Maksim | 2025-07-28 | 2025-08-24 | 26 | 100% | bar: WEEK 1 R to WEEK 2 F; WEEK 6 R
1.3 | Group Contract | EVERYONE | 2025-07-28 | 2025-08-24 | 26 | 100% | bar: WEEK 1 R; WEEK 6 R
1.4 | Off-class meeting agreement | EVERYONE | 2025-07-28 | 2025-08-24 | 26 | bar: WEEK 6 R
2 | Project ideation | EVERYONE | 2025-08-07 | 2025-08-24 | 17 | 100%
2.1 | Individual ideation | EVERYONE | 2025-08-07 | 2025-08-24 | 17 | 100% | bar: WEEK 1 R to WEEK 2 F; WEEK 6 R
2.2 | Idea selection | EVERYONE | 2025-08-07 | 2025-08-24 | 17 | 100% | bar: WEEK 2 M to WEEK 3 R; WEEK 6 R
2.3 | Required sensing research | Aldorino | 2025-08-07 | 2025-08-24 | 17 | 100% | bar: WEEK 3 R to WEEK 4 F; WEEK 6 R
2.4 | Simulation constraints research | Mikhail | 2025-08-07 | 2025-08-24 | 17 | 100% | bar: WEEK 3 R to WEEK 4 F; WEEK 6 R
2.5 | Similar projects research | Nam | 2025-08-07 | 2025-08-24 | 17 | 100% | bar: WEEK 3 R to WEEK 4 F; WEEK 6 R
2.6 | Simulation setup | EVERYONE | 2025-08-07 | 2025-08-24 | 17 | 100% | bar: WEEK 1 T to WEEK 2 F; WEEK 6 R
2.7 | Stakeholder communication | EVERYONE | 2025-08-07 | 2025-08-24 | 17 | 100% | bar: WEEK 6 R
3 | C1 Submission | EVERYONE | 2025-08-14 | 2025-08-25 | 11 | 100%
3.1 | Team & Collaboration | EVERYONE | 2025-08-14 | 2025-08-25 | 11 | 100% | bar: WEEK 3 R to WEEK 4 F; WEEK 6 R
3.2 | Project Direction | Nam + Mike | 2025-08-14 | 2025-08-25 | 11 | 100% | bar: WEEK 3 R to WEEK 4 F; WEEK 6 R
3.3 | System Design | Aldorino | 2025-08-14 | 2025-08-25 | 11 | 100% | bar: WEEK 3 R to WEEK 4 F; WEEK 6 R
3.4 | Planning | Maksim | 2025-08-14 | 2025-08-25 | 11 | 100% | bar: WEEK 3 R to WEEK 4 F; WEEK 6 R
3.5 | Communication | Mikhail | 2025-08-14 | 2025-08-25 | 11 | 100% | bar: WEEK 3 R to WEEK 4 F; WEEK 6 R
3.6 | Generative AI | Nam | 2025-08-14 | 2025-08-25 | 11 | 100% | bar: WEEK 3 R to WEEK 4 F; WEEK 6 R
2 | Phase 2
1 | Project development | EVERYONE | 2025-08-25 | 2025-09-21 | 26 | 0%
1.1 | Import sensing modules | Aldorino | 2025-08-25 | 2025-09-21 | 26 | 0% | bar: WEEK 4 M to WEEK 5 F; WEEK 6 R
1.2 | Seed sensor data in simulation | Aldorino | 2025-08-25 | 2025-09-21 | 26 | 0%
1.3 | Libraries for sensors | Aldorino | 2025-08-25 | 2025-09-21 | 26 | 0% | bar: WEEK 6 R; WEEK 7 M to WEEK 7 F
1.4 | Obstacle detection algorithm | Nam | 2025-08-25 | 2025-09-21 | 26 | 0% | bar: WEEK 4 M to WEEK 5 F; WEEK 6 R
1.5 | Forest navigation development | Nam | 2025-08-25 | 2025-09-21 | 26 | 0%
1.6 | Behaviour statuses of system | Nam | 2025-08-25 | 2025-09-21 | 26 | 0% | bar: WEEK 6 R; WEEK 7 M to WEEK 7 F
1.7 | Import of forest models | Mikhail | 2025-08-25 | 2025-09-21 | 26 | 0% | bar: WEEK 4 M to WEEK 5 F; WEEK 6 R
1.8 | Creation of different worlds | Mikhail | 2025-08-25 | 2025-09-21 | 26 | 0%
1.9 | Variable environment generation | Mikhail | 2025-08-25 | 2025-09-21 | 26 | 0% | bar: WEEK 6 R; WEEK 7 M to WEEK 7 F
1.11 | GUI drafting | Maksim | 2025-08-25 | 2025-09-21 | 26 | 0% | bar: WEEK 6 R
1.12 | GUI controls programming | Maksim | 2025-08-25 | 2025-09-21 | 26 | 0% | bar: WEEK 4 M to WEEK 5 F; WEEK 6 R
1.13 | Populating GUI with map data | Maksim | 2025-08-25 | 2025-09-21 | 26 | 0%
1.14 | Status and camera feed in GUI | Maksim | 2025-08-25 | 2025-09-21 | 26 | 0% | bar: WEEK 6 R; WEEK 7 M to WEEK 7 F
1.15 | Stakeholder communication | EVERYONE | 2025-08-25 | 2025-09-21 | 26 | 0% | bar: WEEK 5 R; WEEK 6 R; WEEK 7 R; WEEK 8 R
2 | C2 Submission | EVERYONE | 2025-09-01 | 2025-09-08 | 7 | 0%
2.1 | Preparation of slides | EVERYONE | 2025-09-01 | 2025-09-08 | 7 | 0%
2.2 | Stakeholder resentation | EVERYONE | 2025-09-07 | 2025-09-08 | 1 | 0% | bar: WEEK 6 R; WEEK 7 M
3 | C3 Submission | EVERYONE | 2025-09-01 | 2025-09-15 | 14 | 0%
3.1 | Preparation of report | EVERYONE | 2025-09-01 | 2025-09-15 | 14 | 0% | bar: WEEK 6 M to WEEK 7 F